## By Date
Class Schedule Production Timeline - Fall 2018
Last Updated: 2/20/18 (JBM)
Date |  | Responsibility | Activity
November 2017
2017-09-25 | Mon. | Erica Marrone, Curriculum Analyst | Email CALT document to Schedule Preparers and request confirmation of dates
2017-09-25 | Mon. | Jeff Mills, Systems Support Analyst | Setup reminder emails for Publications Editor and Supervisor
2017-10-03 | Tue. | Jeff Mills, Systems Support Analyst | Email printers proof distribution to Schedule Preparers. Update distribution list for Fall 2018 process requisitions.
2017-10-18 | Wed. | VPIs | Return CALT dates and parameters to Shelly Hess
2017-10-19 | Thur. | Erica Marrone, Curriculum Analyst | Deliver CALT dates to Student Services
2017-11-03 | Fri. | Information Technology | Roll Fall 2017 to Fall 2018 Scheduler Project available for input after the roll
2017-11-06 | Mon. | Student Services Analyst | Make Scheduler available (Melonie)
2017-11-06 | Mon. | Department Chairs | Update Fall 2018 class information in ISIS/Scheduler
2017-11-06 | Mon. | Schedule Preparers | Update Fall 2018 class information in ISIS
December 2017
2017-12-08 | Fri. | IT Production Control | Download (PSISCS1O ) Fall 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM – will not include updated full course title and short course description
February 2018
2018-02-16 | Fri. | Holiday - Lincoln's Birthday
2018-02-19 | Mon. | Holiday - Washington's Birthday
2018-02-22 | Thu. | Team of Schedule Preparers | Scheduler availability ends for fall 2018
2018-02-23 | Fri. | Jeff Mills, Systems Support Analyst | Run B2511 and 2505 printers proofs for fall 2018
2018-02-26 | Mon. | Team of Schedule Preparers | Use B2511 and B2505 printers proofs to enter fall 2018 class data manually into Campus Solutions begins.
March 2018
3/26-3/31 | Mon.Sat. | Colleges Closed - Spring Break
2018-03-30 | Fri. | Holiday - Cesar Chavez
April 2018
2018-04-12 | Thur. | District Graphic Artist | Select photos for cover
2018-04-12 | Thur. | Director, Communications and Public Relations | Review Chancellor's Welcome Message and provide updates to Multimedia Specialist
2018-04-12 | Thur. | Student Services Support Technician | Deliver modifications to inside front cover to District Graphic Artist
2018-04-12 | Thur. | Stephanie Bulger, Vice Chancellor, Instructional Services | Report any changes to Corporate Council logos to District Graphic Artist (Claudia Azcona-Mercado)
2018-04-13 | Fri. | Student Systems Support Technician | Deliver highlighted changes in MS Word (final narrative, academic calendars/common pages, fee information, policy statements, etc. for Combo class schedules) to Eric Nunes, Multimedia Specialist
2018-04-13 | Fri. | TBD | Download Fall 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM – will not include updated full course title and short course description
2018-04-16 | Mon. | Jeff Mills, Systems Support Analyst | Turn on course listings, and email Schedule Preparers that the listings are available.
2018-04-16 | Mon. | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Website (after 8:30 AM)
2018-04-26 | Thu. | Honors Coordinators – Kelly Mayhew & Hector Martinez | Deliver changes to District Honors page to Eric Nunes, Multimedia Specialist
2018-04-26 | Thur. | Dean, Online Instruction and Distributed Learning | Deliver changes to online learning common page (page prior to course listings) to Eric Nunes, Multimedia Specialist
2018-04-30 | Mon. | Publications Editor & Supervisor | Email Sun Distributing list to PIOs for review and update
May 2018
2018-05-04 | Fri. | Public Information Officers | Return review Sun Distributing list to Publications Editor & Supervisor
2018-05-07 | Mon. | Erica Marrone, Curriculum Analyst | Email IT Web Staff, request Fall 2018 test term be loaded into the test schedule (if ISIS is used to produce printed class schedule).
2018-05-11 | Fri. | Schedule Preparers | Input Deadline Final changes to class schedule in CS prior to download. No changes after 5:00 PM
| Fri. | Jeff Mills, Systems Support Analyst | Execute run control in CS. Upload Fall 2018 course listings to ISCLASS WEB SERVER
2018-05-11 | Fri. | Continuing Education Graphic Artist | Deliver Continuing Education pages (in pdf format) to Eric Nunes, Multimedia Specialist
2018-05-12 | Fri. | Eric Nunes, Multimedia Specialist | Compile common pages and International Ed/Honors ads (in InDesign format) to Jeff Mills, Systems Support Analyst--if needed for paging
2018-05-11 | Fri. | District Graphic Artist | Present draft of updated cover to Director
2018-05-14 | Mon. | Jeff Mills, Systems Support Analyst | Execute run control. Upload course listings to ISLCASS. Email Schedule Preparers that the listings are available
2018-05-14 | Mon. | Eric Nunes, Multimedia Specialist | Email Military Ed listings and Online course listings to Schedule Preparers for review
2018-05-14 | Mon. | Erica Marrone, Curriculum Analyst | Review requisite and course families in CS.
2018-05-14 | Mon. | Bookstore Supervisor | Receives Nebraska books interface file
2018-05-14 | Mon. | Schedule Preparers | Print and distribute course listings. Coordinate review of content with department chairs and campus deans. Update content changes/corrections. Report errors regarding titles to Instructional Services
2018-05-14 | Mon. | TBD by each College | Deliver Changes to Off-Campus locations to Eric Nunes, Eric Nunes, Multimedia Specialist (City-Catherine Shafer; Mesa-Arlis Svedberg; Miramar-Shaunna Elmone)
2018-05-14 | Mon. | Eric Nunes, Multimedia Specialist | Notify Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2018-05-14 | Mon. | Student Systems Support Technician | Reviews draft of narrative and academic calendar (first review)
2018-05-18 | Fri. | Schedule Preparers | Input final corrections to class schedule in CS prior to final download. No changes after 5:00 PM. This is the final input deadline CS data to be included in printed schedule. Any changes after 5pm will be reflected in online schedule, but not printed schedule1
2018-05-18 | Fri. | Eric Nunes, Multimedia Specialist | Email updated Military Ed page to Schedule Preparers and Director, Off-Campus Programs (Catherine Shafer).
2018-05-18 | Fri. | Student Systems Support Technician | First review changes due back to Eric Nunes, Multimedia Specialist (additional changes after this date may be made with SDCCD class schedule proofing sign-off form)
2018-05-18 | Fri - Wed | Schedule Preparers | Final formatting of course listings in MS Word
2018-05-18 | Fri. | IT Production Control | Final Download Fall 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM (prior to 6:00 AM on Mon.)
2018-05-21 | Mon. | Jeff Mills, Systems Support Analyst | Upload course listings to ISCLASS, turn on course listings, and email Schedule Preparers that the listings are available
2018-05-21 | Tue. | Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Schedule Website (after 8:30 AM)
2018-05-23 | Wed. | Schedule Preparers | Deliver MS Word formatted course listings to PIOs (1st proof)
2018-05-23 | Wed. | Schedule Preparers, Direct of Off-Campus Programs | Email corrections to Military Ed page to Eric Nunes, Multimedia Specialist
2018-05-23 | Wed. | Schedule Preparers | Add comments to online course listings file, make corrections/changes, and email file to Eric Nunes, Multimedia Specialist
2018-05-23 | Wed. | District Graphic Artist | Proof of final cover art due. Beresford/Chancellor signoff
2018-05-24 | Thur. | District Graphic Artist | Deliver final cover art to Systems Support Analyst
2018-05-24 | Thur. | Eric Nunes, Multimedia Specialist | Integrate changes to online listings from all three colleges into InDesign
2018-05-24 | Thur. | Information Officers | Import course listings into InDesign and format
2018-05-28 | Mon | Holiday - Memorial Day
2018-05-29 | Tues. | Erica Marrone, Curriculum Analyst | Determine prerequisites changes
2018-05-30 | Wed. | Eric Nunes, Multimedia Specialist | Deliver online course listings proof to Jeff Mills, Systems Support Analyst
2018-05-30 | Wed. | Vice Presidents of Student Services | Email campus quantities needed to Jeff Mills, Systems Support Analyst
2018-05-30 | Wed. | Jeff Mills, Systems Support Analyst | Upload final cover art to commercial printers.
2018-05-31 | Thur. | Information Officers | Deliver proofs to Schedule Preparers/VP Instruction-first review
2018-05-31 | Thur. | Eric Nunes, Multimedia Specialist | Email online course listings PDF to Schedule Preparers for review
June 2018
2018-06-01 | Fri. | Jeff Mills, Systems Support Analyst | Execute run control in CS, provide updated section comments to Shelly/Trila.
2018-06-04 | Mon. | Publications Editor & Supervisor | Email updated delivery list to Sun Distributing
2018-06-05 | Tues. | Schedule Preparers | Return corrected page proofs to PIOs in AM, return online listings PDF with any changes to Eric Nunes, Multimedia Specialist
2018-06-05 | Tues. | Erica Marrone, Curriculum Analyst | Review course descriptions in online class schedule and make corrections where necessary
2018-06-06 | Wed. | Information Officers / VP’s Instruction | Deliver campus page proofs in hard copy and InDesign digital file to Eric Nunes, Multimedia Specialist in the AM
2018-06-06 | Wed. | Advantage Printers | Deliver cover digital blueline to Jeff Mills, Systems Support Analyst
2018-06-08 | Fri. | Eric Nunes, Multimedia Specialist | Notify campus Information Officers and Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2018-06-08 | Fri. | Student Systems Support Technician/Information Officers/Eric Nunes, Multimedia Specialist | Proof combo page proofs in Instructional Services-check calendars, narrative, and legal information specifically. Distribute, complete, and retain SDCCD sign-off forms. Update In Design files with help from System Support Analyst (Final Proof--All changes must be made by 5:00 pm)
2018-06-08 | Fri. | Shelly Hess | TBD - Email corrected comments to Schedule Preparers to update ISIS.
2018-06-12 | Tues. | Mail Room Clerk | Prepare Postal Form for mailing combo schedules
2018-06-13 | Wed. | Advantage Printers | Pick up combo page proofs, digital files, from Instructional Services in the PM 2
2018-06-15 | Fri. | Jeff Mills, Systems Support Analyst | Remind the Duplicating Supervisor to make sure that sufficient funds are in the postal account to cover the cost of the class schedule mailing
2018-06-18 | Mon. | TBD | Provide public access to CS online class schedule through the district portal
2018-06-18 | Mon. | Advantage Printers | Deliver combo schedule digital bluelines and cover color key to Instructional Services 2
2018-06-18 | Mon. | Eric Nunes, Multimedia Specialist | Notify campus Information Officers and Student Services’ staff. Final proofing. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2018-06-19 | Tues. | Advantage Printers | Pick up reviewed bluelines from Instructional Services
2018-06-26 | Tues. | Advantage Printers | Deliver combo schedules to District sites and Post Office, and combo schedules to Student Services 2
July 2018
2018-07-04 | Wed. | Legal Holiday - Independence Day
2018-07-18 | Mon. | Student Services | Fall 2018 registration by appointment begins
August 2018
2018-08-08 | Wed. | Jeff Mills, Systems Support Analyst | Check schedule quantities at the Warehouse
September 2018
2018-09-07 | Fri. | Jeff Mills, Systems Support Analyst | Contact Warehouse to recycle remaining schedules

## Responsibility
Date |  | Responsibility | Activity
2018-06-06 | Wed. | Advantage Printers | Deliver cover digital blueline to Jeff Mills, Systems Support Analyst
2018-06-13 | Wed. | Advantage Printers | Pick up combo page proofs, digital files, from Instructional Services in the PM 2
2018-06-18 | Mon. | Advantage Printers | Deliver combo schedule digital bluelines and cover color key to Instructional Services 2
2018-06-19 | Tues. | Advantage Printers | Pick up reviewed bluelines from Instructional Services
2018-06-26 | Tues. | Advantage Printers | Deliver combo schedules to District sites and Post Office, and combo schedules to Student Services 2
2018-05-14 | Mon. | Bookstore Supervisor | Receives Nebraska books interface file
2018-05-21 | Tue. | Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Schedule Website (after 8:30 AM)
3/26-3/31 | Mon.Sat. | Colleges Closed - Spring Break
2018-05-11 | Fri. | Continuing Education Graphic Artist | Deliver Continuing Education pages (in pdf format) to Eric Nunes, Multimedia Specialist
2018-04-26 | Thur. | Dean, Online Instruction and Distributed Learning | Deliver changes to online learning common page (page prior to course listings) to Eric Nunes, Multimedia Specialist
2017-11-06 | Mon. | Department Chairs | Update Fall 2018 class information in ISIS/Scheduler
2018-04-12 | Thur. | Director, Communications and Public Relations | Review Chancellor's Welcome Message and provide updates to Multimedia Specialist
2018-04-12 | Thur. | District Graphic Artist | Select photos for cover
2018-05-11 | Fri. | District Graphic Artist | Present draft of updated cover to Director
2018-05-23 | Wed. | District Graphic Artist | Proof of final cover art due. Beresford/Chancellor signoff
2018-05-24 | Thur. | District Graphic Artist | Deliver final cover art to Systems Support Analyst
2018-05-12 | Fri. | Eric Nunes, Multimedia Specialist | Compile common pages and International Ed/Honors ads (in InDesign format) to Jeff Mills, Systems Support Analyst--if needed for paging
2018-05-14 | Mon. | Eric Nunes, Multimedia Specialist | Email Military Ed listings and Online course listings to Schedule Preparers for review
2018-05-14 | Mon. | Eric Nunes, Multimedia Specialist | Notify Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2018-05-18 | Fri. | Eric Nunes, Multimedia Specialist | Email updated Military Ed page to Schedule Preparers and Director, Off-Campus Programs (Catherine Shafer).
2018-05-24 | Thur. | Eric Nunes, Multimedia Specialist | Integrate changes to online listings from all three colleges into InDesign
2018-05-30 | Wed. | Eric Nunes, Multimedia Specialist | Deliver online course listings proof to Jeff Mills, Systems Support Analyst
2018-05-31 | Thur. | Eric Nunes, Multimedia Specialist | Email online course listings PDF to Schedule Preparers for review
2018-06-08 | Fri. | Eric Nunes, Multimedia Specialist | Notify campus Information Officers and Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2018-06-18 | Mon. | Eric Nunes, Multimedia Specialist | Notify campus Information Officers and Student Services’ staff. Final proofing. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2017-09-25 | Mon. | Erica Marrone, Curriculum Analyst | Email CALT document to Schedule Preparers and request confirmation of dates
2017-10-19 | Thur. | Erica Marrone, Curriculum Analyst | Deliver CALT dates to Student Services
2018-05-07 | Mon. | Erica Marrone, Curriculum Analyst | Email IT Web Staff, request Fall 2018 test term be loaded into the test schedule (if ISIS is used to produce printed class schedule).
2018-05-14 | Mon. | Erica Marrone, Curriculum Analyst | Review requisite and course families in CS.
2018-05-29 | Tues. | Erica Marrone, Curriculum Analyst | Determine prerequisites changes
2018-06-05 | Tues. | Erica Marrone, Curriculum Analyst | Review course descriptions in online class schedule and make corrections where necessary
2018-03-30 | Fri. | Holiday - Cesar Chavez
2018-02-16 | Fri. | Holiday - Lincoln's Birthday
2018-05-28 | Mon | Holiday - Memorial Day
2018-02-19 | Mon. | Holiday - Washington's Birthday
2018-04-26 | Thu. | Honors Coordinators – Kelly Mayhew & Hector Martinez | Deliver changes to District Honors page to Eric Nunes, Multimedia Specialist
2018-05-24 | Thur. | Information Officers | Import course listings into InDesign and format
2018-05-31 | Thur. | Information Officers | Deliver proofs to Schedule Preparers/VP Instruction-first review
2018-06-06 | Wed. | Information Officers / VP’s Instruction | Deliver campus page proofs in hard copy and InDesign digital file to Eric Nunes, Multimedia Specialist in the AM
2017-11-03 | Fri. | Information Technology | Roll Fall 2017 to Fall 2018 Scheduler Project available for input after the roll
2017-12-08 | Fri. | IT Production Control | Download (PSISCS1O ) Fall 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM – will not include updated full course title and short course description
2018-05-18 | Fri. | IT Production Control | Final Download Fall 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM (prior to 6:00 AM on Mon.)
2017-09-25 | Mon. | Jeff Mills, Systems Support Analyst | Setup reminder emails for Publications Editor and Supervisor
2017-10-03 | Tue. | Jeff Mills, Systems Support Analyst | Email printers proof distribution to Schedule Preparers. Update distribution list for Fall 2018 process requisitions.
2018-02-23 | Fri. | Jeff Mills, Systems Support Analyst | Run B2511 and 2505 printers proofs for fall 2018
2018-04-16 | Mon. | Jeff Mills, Systems Support Analyst | Turn on course listings, and email Schedule Preparers that the listings are available.
2018-05-11 | Fri. | Jeff Mills, Systems Support Analyst | Execute run control in CS. Upload Fall 2018 course listings to ISCLASS WEB SERVER
2018-05-14 | Mon. | Jeff Mills, Systems Support Analyst | Execute run control. Upload course listings to ISLCASS. Email Schedule Preparers that the listings are available
2018-05-21 | Mon. | Jeff Mills, Systems Support Analyst | Upload course listings to ISCLASS, turn on course listings, and email Schedule Preparers that the listings are available
2018-05-30 | Wed. | Jeff Mills, Systems Support Analyst | Upload final cover art to commercial printers.
2018-06-01 | Fri. | Jeff Mills, Systems Support Analyst | Execute run control in CS, provide updated section comments to Shelly/Trila.
2018-06-15 | Fri. | Jeff Mills, Systems Support Analyst | Remind the Duplicating Supervisor to make sure that sufficient funds are in the postal account to cover the cost of the class schedule mailing
2018-08-08 | Wed. | Jeff Mills, Systems Support Analyst | Check schedule quantities at the Warehouse
2018-09-07 | Fri. | Jeff Mills, Systems Support Analyst | Contact Warehouse to recycle remaining schedules
2018-07-04 | Wed. | Legal Holiday - Independence Day
2018-06-12 | Tues. | Mail Room Clerk | Prepare Postal Form for mailing combo schedules
2018-05-04 | Fri. | Public Information Officers | Return review Sun Distributing list to Publications Editor & Supervisor
2018-04-30 | Mon. | Publications Editor & Supervisor | Email Sun Distributing list to PIOs for review and update
2018-06-04 | Mon. | Publications Editor & Supervisor | Email updated delivery list to Sun Distributing
2017-11-06 | Mon. | Schedule Preparers | Update Fall 2018 class information in ISIS
2018-05-11 | Fri. | Schedule Preparers | Input Deadline Final changes to class schedule in CS prior to download. No changes after 5:00 PM
2018-05-14 | Mon. | Schedule Preparers | Print and distribute course listings. Coordinate review of content with department chairs and campus deans. Update content changes/corrections. Report errors regarding titles to Instructional Services
2018-05-18 | Fri. | Schedule Preparers | Input final corrections to class schedule in CS prior to final download. No changes after 5:00 PM. This is the final input deadline CS data to be included in printed schedule. Any changes after 5pm will be reflected in online schedule, but not printed schedule1
2018-05-18 | Fri - Wed | Schedule Preparers | Final formatting of course listings in MS Word
2018-05-23 | Wed. | Schedule Preparers | Deliver MS Word formatted course listings to PIOs (1st proof)
2018-05-23 | Wed. | Schedule Preparers | Add comments to online course listings file, make corrections/changes, and email file to Eric Nunes, Multimedia Specialist
2018-06-05 | Tues. | Schedule Preparers | Return corrected page proofs to PIOs in AM, return online listings PDF with any changes to Eric Nunes, Multimedia Specialist
2018-05-23 | Wed. | Schedule Preparers, Direct of Off-Campus Programs | Email corrections to Military Ed page to Eric Nunes, Multimedia Specialist
2018-04-16 | Mon. | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Website (after 8:30 AM)
2018-06-08 | Fri. | Shelly Hess | TBD - Email corrected comments to Schedule Preparers to update ISIS.
2018-04-12 | Thur. | Stephanie Bulger, Vice Chancellor, Instructional Services | Report any changes to Corporate Council logos to District Graphic Artist (Claudia Azcona-Mercado)
2018-07-08 | Mon. | Student Services | Fall 2018 registration by appointment begins
2017-11-06 | Mon. | Student Services Analyst | Make Scheduler available (Melonie)
2018-04-12 | Thur. | Student Services Support Technician | Deliver modifications to inside front cover to District Graphic Artist
2018-04-13 | Fri. | Student Systems Support Technician | Deliver highlighted changes in MS Word (final narrative, academic calendars/common pages, fee information, policy statements, etc. for Combo class schedules) to Eric Nunes, Multimedia Specialist
2018-05-14 | Mon. | Student Systems Support Technician | Reviews draft of narrative and academic calendar (first review)
2018-05-18 | Fri. | Student Systems Support Technician | First review changes due back to Eric Nunes, Multimedia Specialist (additional changes after this date may be made with SDCCD class schedule proofing sign-off form)
2018-06-08 | Fri. | Student Systems Support Technician/Information Officers/Eric Nunes, Multimedia Specialist | Proof combo page proofs in Instructional Services-check calendars, narrative, and legal information specifically. Distribute, complete, and retain SDCCD sign-off forms. Update In Design files with help from System Support Analyst (Final Proof--All changes must be made by 5:00 pm)
2018-04-13 | Fri. | TBD | Download Fall 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM – will not include updated full course title and short course description
2018-06-18 | Mon. | TBD | Provide public access to CS online class schedule through the district portal
2018-05-14 | Mon. | TBD by each College | Deliver Changes to Off-Campus locations to Eric Nunes, Eric Nunes, Multimedia Specialist (City-Catherine Shafer; Mesa-Arlis Svedberg; Miramar-Shaunna Elmone)
2018-02-22 | Thu. | Team of Schedule Preparers | Scheduler availability ends for fall 2018
2018-02-26 | Mon. | Team of Schedule Preparers | Use B2511 and B2505 printers proofs to enter fall 2018 class data manually into Campus Solutions begins.
2018-05-30 | Wed. | Vice Presidents of Student Services | Email campus quantities needed to Jeff Mills, Systems Support Analyst
2017-10-18 | Wed. | VPIs | Return CALT dates and parameters to Shelly Hess

## Milestones
Major Milestones for Fall 2018
Dates | Description
2017-11-03 | Roll Forward Fall 2017 to Fall 2018
2017-11-06 | The Scheduler available
11/6/17 - 1/12/18 | Update Fall 2018 class information in ISIS/Scheduler
2017-12-08 | Use ISIS to download course listings (tapecut)
2018-02-22 | Scheduler availability ends for Fall 2018
2018-02-23 | Run B2511s and B2505 printers proofs
2018-04-13 | Student Services Changes
2018-04-13 | First Download
2018-05-11 | Second Download
2018-05-14 | Student Services (1st Review)
2018-05-18 | Student Services 1st review due back to Instructional Services
2018-05-18 | Final Download
2018-06-01 | PIOs First Page Proof
2018-06-05 | Page Proofs Due
2018-06-06 | Cover blueline Due
2018-06-09 | Review Final Page Proofs
2018-06-19 | Bluelines Due (PIOs and Student Services Proof)
2018-06-26 | Schedules Delivered
2018-07-18 | Registration by Appointment Begins