## By Date
Class Schedule Production Timeline - Spring 2018 with Intersession
Last Updated: 5/24/17
Date |  | Responsibility | Activity
2017-04-01
2017-04-12 | Wed | Erica Marrone, Curriculum Analyst | Email CALT document to Schedule Preparers and request confirmation of dates
2017-04-12 | Wed | Jeff Mills, Systems Support Analyst | Setup task reminders for Publications Editor and Supervisor
2017-04-28 | Fri | Jeff Mills, Systems Support Analyst | Email printers proof distribution to Schedule Preparers. Update distribution list for Spring 2018 process requisitions.
2017-05-01
2017-05-05 | Fri | Erica Marrone, Curriculum Analyst | Deliver CALT dates to Student Services
2017-05-29 | Mon | Holiday - Memorial Day
2017-06-01
2017-06-09 | Fri | Information Technology | Roll Spring 2017 to Spring 2018 Scheduler Project Available for Input After the Roll
2017-06-12 | Mon | Student Services Analyst (Melonie) | Scheduler available
2017-07-01
2017-07-04 | Tue | Holiday - Independence Day
2017-08-01
2017-08-09 | Wed | Student Services Support Technician | Deliver cover changes to District Graphic Artist
2017-08-10 | Thu | District Graphic Artist | Select photos for cover
2017-08-10 | Thu | Director, Communications and Public Relations | Review Chancellor's Welcome Message and provide updates to Multimedia Specialist
2017-08-10 | Thu | Dean, Economic Development | Report any changes to Corporate Council logos to District Graphic Designer (Brenda Manzelli)
2017-08-11 | Fri | Student Systems Support Technician | Deliver highlighted changes in MS Word (final narrative, academic calendars/common pages, fee information, policy statements, etc. for Combo class schedules) to Multimedia Specialist
2017-08-11 | Fri. | IT Production Control | Download (PSISCS1O ) Spring 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM (prior to 6:00 AM on Mon. Aug ??20) – will not include updated full course title and short course description
2017-08-14 | Mon | Jeff Mills, Systems Support Analyst | Run macros in ISCLASS, turn on course listings, and email Schedule Preparers that the listings are available.
2017-08-14 | Mon. | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Website (after 8:30 AM)
2017-09-01
2017-09-04 | Mon | Holiday - Labor Day
2017-09-08 | Fri | Honors Coordinators – Wendy Smith & Leticia Lopez | Deliver changes to District Honors page to Multimedia Specialist
2017-09-08 | Fri. | Dean, Online Instruction and Distributed Learning | Deliver changes to online learning common page (page prior to course listings) to Multimedia Specialist
2017-09-08 | Fri. | Continuing Education Graphic Artist | Deliver Continuing Education pages (in pdf format) to Multimedia Specialist
2017-09-08 | Fri. | Publications Editor & Supervisor | Email Sun Distributing list to PIOs for review and update
2017-09-08 | Fri. | Public Information Officers | Return review Sun Distributing list to Publications Editor & Supervisor
2017-09-11 | Mon | Erica Marrone, Curriculum Analyst | Run CurricUNET extract process for long titles (printed schedule). Review long course titles.
2017-09-13 | Wed | Erica Marrone, Curriculum Analyst | Verify accuracy of long titles and notify IT to upload from test to production
2017-09-15 | Fri | IT Web Staff | Upload Spring 2018 long course titles to Production SQL Master table for ISCLASS--CurricUNET extract process for printed class schedule
2017-09-15 | Fri. | Multimedia Specialist | Compile common pages and International Ed/Honors ads (in InDesign format) in case needed for schedule pagination
2017-09-15 | Fri. | District Graphic Artist | Present draft of updated cover to Director
2017-09-15 | Fri | Schedule Preparers | Input Final changes to class schedule prior to download. No changes after 5:00 PM
2017-09-15 | Fri. | IT Production Control | Download (PSISCS1O ) Spring 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM
2017-09-18 | Mon | Jeff Mills, Systems Support Analyst | Run macros in ISCLASS, turn on course listings, and email Schedule Preparers that the listings are avialable
2017-09-18 | Mon. | Eric Nunes, Multimedia Specialist | Email Military Ed listings and Online course listings to Schedule Preparers for review
2017-09-18 | Mon. | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Schedule Website (after 8:30 AM)
2017-09-18 | Mon. | Schedule Preparers | Print and distribute course listings. Coordinate review of ISIS content with department chairs and campus deans. Update content changes/corrections in ISIS. Report errors regarding title and short course descriptions to Instructional Services
2017-09-18 | Mon. | TBD by each College | Deliver Changes to Off-Campus locations to Multimedia Specialist (City-Jeanie Tyler; Mesa-Arlis Svedberg; Miramar-Terrie Hubbard)
2017-09-20 | Wed | Student Systems Support Technician | Reviews first draft of narrative (First Review)
2017-09-20 | Tues. | Eric Nunes, Multimedia Specialist | Notify Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2017-09-21 | Thu | Student Systems Support Technician | First review changes due back to IS Multimedia Specialist (additional changes after this date may be made with SDCCD class schedule proofing sign-off form)
2017-09-22 | Fri | Schedule Preparers | Input final corrections to class schedule prior to final download. No changes after 5:00 PM. This is the final input deadline for ISIS data to be included in printed schedule. Any changes after 5pm will be reflected in online schedule, but not printed schedule1
2017-09-22 | Fri | IT Production Control | Final Download (PSISCS1O ) Spring 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM
2017-09-22 | Fri. | Eric Nunes, Multimedia Specialist | Email updated Military Ed page to Schedule Preparers and Director, Off-Campus Programs (Jeanie Tyler).
2017-09-25 | Mon | Jeff Mills, Systems Support Analyst | Run macros in ISCLASS, turn on course listings, and email Schedule Preparers that the listings are available.
2017-09-25 | Mon | Erica Marrone, Curriculum Analyst | Run CurricUNET extract process to download clas_course data and clas_reqs data to 10.1.1.136 server (online class schedule). Review requisite and course description information in the test system--CurricUNET extract process for the Online Class Schedule. When accuracy is verified then notify IT to move to Production.
2017-09-25 | Mon | Erica Marrone, Curriculum Analyst | Request from Martin, copy IT Web Staff, test term be loaded into test scheduled.
2017-09-25 | Mon | Erica Marrone, Curriculum Analyst | Run CurricUNET extract process to download clas_course data and clas_reqs data to 10.1.1.136 server (online class schedule). Review requisite and course description information in the test system--CurricUNET extract process for the Online Class Schedule. When accuracy is verified then notify IT to move to Production.
2017-09-25 | Mon | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from IS Class Schedule Website (after 8:30 AM)
2017-09-25 | Mon | Schedule Preparers | Begin final formatting of course listings in MS Word
2017-09-28 | Thu | Schedule Preparers | Deliver MS Word formatted course listings to PIOs (1st proof)
2017-09-28 | Thu | Schedule Preparers, Director of Off-Campus Programs | Email corrections to Military Ed page to Multimedia Specialist
2017-09-28 | Thu | Schedule Preparers | Add comments to online course listings file, make corrections/changes, and email file to Multimedia Specialist
2017-09-29 | Fri | IT Web Staff | Upload Spring 2018 course description file to Online Class Schedule test system--CurricUNET extract process for the Online Class Schedule
2017-10-01
2017-10-06 | Fri | District Graphic Artist | Final cover art due. Beresford/Chancellor signoff
2017-10-06 | Thur. | Multimedia Specialist | Integrate changes to online listings from all three colleges into InDesign
2017-10-13 | Fri | Information Officers | Deliver proofs to Schedule Preparers/VP Instruction-final review (First Review)
2017-10-13 | Thur. | Multimedia Specialist | Email online course listings PDF to Schedule Preparers for review
2017-10-17 | Tue | Schedule Preparers | Return corrected page proofs to PIOs in AM, return online listings PDF with any changes to Multimedia Specialist
2017-10-17 | Tue | Erica Marrone, Curriculum Analyst | Download ISCLASS section comments for review. Send corrections to Schedule Preparers to update ISIS.
2017-10-17 | Tue | Erica Marrone, Curriculum Analyst | Deliver Prerequisites changes to Student Systems Support Technician
2017-10-19 | Thu | Multimedia Specialist | Deliver online course listings proof to Jeff Mills, Systems Support Analyst
2017-10-19 | Thu | Information Officers / VP’s Instruction | Deliver campus pages in hard copy and InDesign digital file to Jeff Mills, Systems Support Analyst in the AM
2017-10-19 | Thu | Multimedia Specialist | Compiles sections of the combo and repaginates
2017-10-19 | #NAME? | Jeff Mills, Systems Support Analyst | Email request for campus quantities to VPSSs
2017-10-20 | Fri | Erica Marrone, Curriculum Analyst | Send ISCLASS section comments corrections to Schedule Preparers to update ISIS
2017-10-20 | Fri | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2017-10-20 | Fri | Student Systems Support Technician/Information Officers/Multimedia Specialist | Proof combo page proofs in Instructional Services-check calendars, narrative, and legal information specifically. Distribute, complete, and retain SDCCD sign-off forms. Update In Design files with help from System Support Analyst (Final Proof--All changes must be made by 5:00 pm)
2017-10-25 | Wed | Vice Presidents of Student Services | Email campus quantities needed to Jeff Mills, Systems Support Analyst.
2017-10-25 | Wed | Mail Room Clerk | Prepare Postal Form for mailing combo schedules
2017-10-26 | Thu | San Dieguito Printers | Pick up combo page proofs, digital files, cover art, from Instructional Services in the PM 2
2017-10-27 | Fri | Erica Marrone, Curriculum Analyst | Notify IT that clas_course data and clas_reqs data is ready to be moved from Test to Production
2017-10-30 | Mon | Jeff Mills, Systems Support Analyst | Remind the Duplicating Supervisor to make sure that sufficient funds are in the postal account to cover the cost of the class schedule mailing
2017-10-31 | Tue | San Dieguito Printers | Deliver combo schedule digital bluelines and cover color key to Instructional Services 2
2017-10-31 |  | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff. Final proofing. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2017-10-31 |  | Student Systems Support Technician | Post class schedule to the web
2017-11-01
2017-11-01 | Wed | San Dieguito Printers | Pick up reviewed bluelines from Instructional Services
2017-11-08 | Wed | San Dieguito Printers | Deliver combo schedules to District sites and Post Office, and minimum of 600 combo schedules to Student Services 2
2017-11-10 | Fri | Holiday - Veterans Day
2017-11-13 | Mon | Student Services | Registration by appointment date (tentative)
2017-12-01
2017-12-07 | Thu | Jeff Mills, Systems Support Analyst | Check schedule quantities at the Warehouse
2018-01-01
2018-01-08 | Mon | Jeff Mills, Systems Support Analyst | Contact Warehouse to recycle remaining schedules
Student Services, District Headquarters
| Student Systems Support Technician |  | Danya Sanchez
| Student Services Analyst |  | Melonie Limtiaco
Instructional Services and Planning, District Headquarters
| Dean, Online Instruction & Learning |  | Kats Gustafson
| Vice Chancellor, Instructional Services & Planning |  | Stephanie Bulger
| Systems Support Analyst |  | Jeff Mills
| Multimedia Specialist |  | Eric Nunes
| Curriculum Analyst |  | Erica Marrone
Communications and Public Relations, District Headquarters
| District Graphic Artist |  | TBD June 5th
| Publications Editor & Supervisor |  | Cesar Gumapas
District Sites (Colleges and CE Campuses)
| IT Production Control |  | District/Miramar
| Information Officers (PIOs) |  | Heidi Bunkowske (City)
Jennifer Kearns (Mesa)
Stephen Quis (Miramar)
Ranessa Ashton (Continuing Education)
| Graphic Artists |  | Kimberly La Rue (City)
Nicholas David (Mesa)
Joan Mize (Miramar)
| Schedule Preparers |  | Kamini Bhakta (City)
Arlis Svedberg (Mesa)
Shaunna Elmone (Miramar)
Off-site Printers
| Advantage/San Dieguito Printers |  | Chris Baker, Mary Lytch
1Production staff (i.e. district and non-district personnel involved in producing class schedules) will not be held accountable for meeting production timelines for information or alterations to the schedule, which are submitted after 5:00 PM on this date.
2We attempt to arrange schedule delivery by 10:00 AM and pick up by 2:00 PM; however this is subject to change depending on conditions at the time. Please contact Instructional Services for more information.

## Responsibility
Class Schedule Production Timeline - Spring 2018 with Intersession
Last Updated: 8/12/2015
Date |  | Responsibility | Activity
2017-04-12 | Wed | Erica Marrone, Curriculum Analyst | Email CALT document to Schedule Preparers and request confirmation of dates
2017-04-12 | Wed | Jeff Mills, Systems Support Analyst | Setup task reminders for Publications Editor and Supervisor
2017-04-28 | Fri | Jeff Mills, Systems Support Analyst | Email printers proof distribution to Schedule Preparers. Update distribution list for Spring 2018 process requisitions.
2017-05-05 | Fri | Erica Marrone, Curriculum Analyst | Deliver CALT dates to Student Services
2017-05-29 | Mon | Holiday - Memorial Day
2017-06-09 | Fri | Information Technology | Roll Spring 2017 to Spring 2018 Scheduler Project Available for Input After the Roll
2017-06-12 | Mon | Student Services Analyst (Melonie) | Scheduler available
2017-07-04 | Tue | Holiday - Independence Day
2017-08-09 | Wed | Student Services Support Technician | Deliver cover changes to District Graphic Artist
2017-08-10 | Thu | Dean, Economic Development | Report any changes to Corporate Council logos to District Graphic Designer (Cesar Gumapus)
2017-08-10 | Thu | Director, Communications and Public Relations | Review Chancellor's Welcome Message and provide updates to Multimedia Specialist
2017-08-10 | Thu | District Graphic Artist | Select photos for cover
2017-08-11 | Fri. | IT Production Control | Download (PSISCS1O ) Spring 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM (prior to 6:00 AM on Mon. Aug ??20) – will not include updated full course title and short course description
2017-08-11 | Fri | Student Systems Support Technician | Deliver highlighted changes in MS Word (final narrative, academic calendars/common pages, fee information, policy statements, etc. for Combo class schedules) to Multimedia Specialist
2017-08-14 | Mon | Jeff Mills, Systems Support Analyst | Run macros in ISCLASS, turn on course listings, and email Schedule Preparers that the listings are available.
2017-08-14 | Mon. | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Website (after 8:30 AM)
2017-09-04 | Mon | Holiday - Labor Day
2017-09-08 | Fri. | Continuing Education Graphic Artist | Deliver Continuing Education pages (in pdf format) to Multimedia Specialist
2017-09-08 | Fri. | Dean, Online Instruction and Distributed Learning | Deliver changes to online learning common page (page prior to course listings) to Multimedia Specialist
2017-09-08 | Fri | Honors Coordinators – Wendy Smith & Leticia Lopez | Deliver changes to District Honors page to Multimedia Specialist
2017-09-08 | Fri. | Public Information Officers | Return review Sun Distributing list to Publications Editor & Supervisor
2017-09-08 | Fri. | Publications Editor & Supervisor | Email Sun Distributing list to PIOs for review and update
2017-09-11 | Mon | Erica Marrone, Curriculum Analyst | Run CurricUNET extract process for long titles (printed schedule). Review long course titles.
2017-09-13 | Wed | Erica Marrone, Curriculum Analyst | Verify accuracy of long titles and notify IT to upload from test to production
2017-09-15 | Fri. | District Graphic Artist | Present draft of updated cover to Director
2017-09-15 | Fri. | IT Production Control | Download (PSISCS1O ) Spring 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM
2017-09-15 | Fri | IT Web Staff | Upload Spring 2018 long course titles to Production SQL Master table for ISCLASS--CurricUNET extract process for printed class schedule
2017-09-15 | Fri. | Multimedia Specialist | Compile common pages and International Ed/Honors ads (in InDesign format) in case needed for schedule pagination
2017-09-15 | Fri | Schedule Preparers | Input Final changes to class schedule prior to download. No changes after 5:00 PM
2017-09-18 | Mon. | Eric Nunes, Multimedia Specialist | Email Military Ed listings and Online course listings to Schedule Preparers for review
2017-09-18 | Mon | Jeff Mills, Systems Support Analyst | Run macros in ISCLASS, turn on course listings, and email Schedule Preparers that the listings are avialable
2017-09-18 | Mon. | Schedule Preparers | Print and distribute course listings. Coordinate review of ISIS content with department chairs and campus deans. Update content changes/corrections in ISIS. Report errors regarding title and short course descriptions to Instructional Services
2017-09-18 | Mon. | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Schedule Website (after 8:30 AM)
2017-09-18 | Mon. | TBD by each College | Deliver Changes to Off-Campus locations to Multimedia Specialist (City-Jeanie Tyler; Mesa-Arlis Svedberg; Miramar-Terrie Hubbard)
2017-09-20 | Tues. | Eric Nunes, Multimedia Specialist | Notify Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2017-09-20 | Wed | Student Systems Support Technician | Reviews first draft of narrative (First Review)
2017-09-21 | Thu | Student Systems Support Technician | First review changes due back to IS Multimedia Specialist (additional changes after this date may be made with SDCCD class schedule proofing sign-off form)
2017-09-22 | Fri. | Eric Nunes, Multimedia Specialist | Email updated Military Ed page to Schedule Preparers and Director, Off-Campus Programs (Jeanie Tyler).
2017-09-22 | Fri | IT Production Control | Final Download (PSISCS1O ) Spring 2018 class schedule to ISCLASS WEB SERVER after 5:00 PM
2017-09-22 | Fri | Schedule Preparers | Input final corrections to class schedule prior to final download. No changes after 5:00 PM. This is the final input deadline for ISIS data to be included in printed schedule. Any changes after 5pm will be reflected in online schedule, but not printed schedule1
2017-09-26 | Tue | Erica Marrone, Curriculum Analyst | Run CurricUNET extract process to download clas_course data and clas_reqs data to 10.1.1.136 server (online class schedule). Review requisite and course description information in the test system--CurricUNET extract process for the Online Class Schedule. When accuracy is verified then notify IT to move to Production.
2017-09-26 | Tue | Erica Marrone, Curriculum Analyst | Request from Martin, copy IT Web Staff, test term be loaded into test scheduled.
2017-09-26 | Tue | Erica Marrone, Curriculum Analyst | Run CurricUNET extract process to download clas_course data and clas_reqs data to 10.1.1.136 server (online class schedule). Review requisite and course description information in the test system--CurricUNET extract process for the Online Class Schedule. When accuracy is verified then notify IT to move to Production.
2017-09-26 | Tue | Jeff Mills, Systems Support Analyst | Run macros in ISCLASS, turn on course listings, and email Schedule Preparers that the listings are available.
2017-09-26 | Tue | Schedule Preparers | Begin final formatting of course listings in MS Word
2017-09-26 | Tue | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from IS Class Schedule Website (after 8:30 AM)
2017-09-28 | Thu | Schedule Preparers | Deliver MS Word formatted course listings to PIOs (1st proof)
2017-09-28 | Thu | Schedule Preparers | Add comments to online course listings file, make corrections/changes, and email file to Multimedia Specialist
2017-09-28 | Thu | Schedule Preparers, Director of Off-Campus Programs | Email corrections to Military Ed page to Multimedia Specialist
2017-09-29 | Fri | IT Web Staff | Upload Spring 2018 course description file to Online Class Schedule test system--CurricUNET extract process for the Online Class Schedule
2017-10-06 | Fri | District Graphic Artist | Final cover art due. Beresford/Chancellor signoff
2017-10-06 | Thur. | Multimedia Specialist | Integrate changes to online listings from all three colleges into InDesign
2017-10-13 | Fri | Information Officers | Deliver proofs to Schedule Preparers/VP Instruction-final review (First Review)
2017-10-13 | Thur. | Multimedia Specialist | Email online course listings PDF to Schedule Preparers for review
2017-10-17 | Tue | Erica Marrone, Curriculum Analyst | Download ISCLASS section comments for review. Send corrections to Schedule Preparers to update ISIS.
2017-10-17 | Tue | Erica Marrone, Curriculum Analyst | Deliver Prerequisites changes to Student Systems Support Technician
2017-10-17 | Tue | Schedule Preparers | Return corrected page proofs to PIOs in AM, return online listings PDF with any changes to Multimedia Specialist
2017-10-19 | Thu | Information Officers / VP’s Instruction | Deliver campus pages in hard copy and InDesign digital file to Jeff Mills, Systems Support Analyst in the AM
2017-10-19 | #NAME? | Jeff Mills, Systems Support Analyst | Email request for campus quantities to VPSSs
2017-10-19 | Thu | Multimedia Specialist | Deliver online course listings proof to Jeff Mills, Systems Support Analyst
2017-10-19 | Thu | Multimedia Specialist | Compiles sections of the combo and repaginates
2017-10-20 | Fri | Erica Marrone, Curriculum Analyst | Send ISCLASS section comments corrections to Schedule Preparers to update ISIS
2017-10-20 | Fri | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2017-10-20 | Fri | Student Systems Support Technician/Information Officers/Multimedia Specialist | Proof combo page proofs in Instructional Services-check calendars, narrative, and legal information specifically. Distribute, complete, and retain SDCCD sign-off forms. Update In Design files with help from System Support Analyst (Final Proof--All changes must be made by 5:00 pm)
2017-10-25 | Wed | Mail Room Clerk | Prepare Postal Form for mailing combo schedules
2017-10-25 | Wed | Vice Presidents of Student Services | Email campus quantities needed to Jeff Mills, Systems Support Analyst.
2017-10-26 | Thu | San Dieguito Printers | Pick up combo page proofs, digital files, cover art, from Instructional Services in the PM 2
2017-10-27 | Fri | Erica Marrone, Curriculum Analyst | Notify IT that clas_course data and clas_reqs data is ready to be moved from Test to Production
2017-10-30 | Mon | Jeff Mills, Systems Support Analyst | Remind the Duplicating Supervisor to make sure that sufficient funds are in the postal account to cover the cost of the class schedule mailing
2017-10-31 |  | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff. Final proofing. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2017-10-31 | Tue | San Dieguito Printers | Deliver combo schedule digital bluelines and cover color key to Instructional Services 2
2017-10-31 |  | Student Systems Support Technician | Post class schedule to the web
2017-11-01 | Wed | San Dieguito Printers | Pick up reviewed bluelines from Instructional Services
2017-11-08 | Wed | San Dieguito Printers | Deliver combo schedules to District sites and Post Office, and minimum of 600 combo schedules to Student Services 2
2017-11-10 | Fri | Holiday - Veterans Day
2017-11-13 | Mon | Student Services | Registration by appointment date
2017-12-07 | Thu | Jeff Mills, Systems Support Analyst | Check schedule quantities at the Warehouse
2018-01-08 | Mon | Jeff Mills, Systems Support Analyst | Contact Warehouse to recycle remaining schedules

## Milestones
Major Milestones for Spring 2018 with Intersession
Dates | Description
2017-06-09 | Roll Forward spring 2016 to spring 2017
2017-08-11 | First Download
2017-08-11 | Student Services changes due
2017-09-15 | Second Download
2017-09-20 | Student Services (1st Review)
2017-09-21 | Student Services 1st review due back to Instructional Services
2017-09-22 | Final Download
2017-10-13 | PIOs First Page Proof due to VPIs
2016-10-19 | Page Proofs Due
2017-10-20 | Review Final Page Proofs
2017-10-31 | Bluelines Due (PIOs and Student Services Proof)
2017-10-31 | Post Online Class Schedule to the web
2017-11-08 | Schedules Delivered
TBD | Registration Begins