## By Date
Class Schedule Production Timeline - Spring 2020 with Intersession
Last Updated: 7/25/19 - jbm
Date |  | Responsibility | Activity
December 2017
2017-12-04 | Mon | Erica Marrone, Curriculum Analyst | Email CALT document to Schedule Preparers and request confirmation of dates
2017-12-18 | Mon | VPIs | Return CALT dates and parameters to Shelly Hess
2017-12-18 | Mon | Erica Marrone, Curriculum Analyst | Deliver CALT dates to Student Services
January 2018
2018-01-12 | Fri | Erica Marrone, Curriculum Analyst | Roll Spring 2018 to Spring 2020 in ISIS Scheduler Project Available for Input After the Roll
2018-01-15 | Mon | Student Services Analyst | Make Scheduler available (Melonie)
2018-01-15 | Mon | Department Chairs | Update Spring 2020 class information in ISIS/Scheduler
1/15 - 5/4 |  | Schedule Preparers | Update Spring 2020 class information in ISIS
2018-05-04 | Fri | Team of Schedule Preparers | Scheduler availability ends for Spring 2020
5/4 - 9/28 |  | Jeff Mills, Systems Support Analyst | Run B2511 and 2505 printers proofs for Spring 2020
5/4 - 9/28 |  | Team of Schedule Preparers | Use B2511 and B2505 printers proofs to enter Spring 2020 class data manually into Campus Solutions begins.
2018-06-08 | Fri | Schedule Preparers | END data entry for Spring 2020 class sections in ISIS
2018-06-19 | Tue | Schedule Preparers | Begin entering Spring 2020 class schedule data in Campus Solutions
2018-07-24 | Tue | IT Production Control? | Class Schedule Report available (replaces printers proofs)
2018-07-28 | Sat | Schedule Preparers | Last day for Spring 2020 class schedule data entry in Campus Solutions at Corporate Ed Center.
May 2019
2019-05-31 | Fri | Erica Marrone, Curriculum Analyst | ISIS Roll Forward Spring 2019 to Spring 2020
July 2019
2019-07-29 | Mon | IT Production Control | Distribute B2505 and B2511 printers proofs to Schedule Preparers
August 2019
2019-08-14 | Wed | Student Services Support Technician | Update Crosswalk Table X_ISCLASS_AE in CS Production environment
2019-08-14 | Wed | Student Services Support Technician | Deliver cover changes to District Graphic Artist
2019-08-15 | Thu | District Graphic Artist | Select photos for cover
2019-08-15 | Thu | Director, Communications and Public Relations | Review Chancellor's Welcome Message and provide updates to Multimedia Specialist
2018-08-22 | Wed | Dean, Workforce Development | Report any changes to Corporate Council logos to District Graphic Designer (Claudia)
2019-08-23 | Fri | Student Systems Support Technician | Deliver highlighted changes in MS Word (final narrative, academic calendars/common pages, fee information, policy statements, etc. for Combo class schedules) to Multimedia Specialist
2019-08-23 | Fri | Schedule Preparers | END data entry for Spring class sections in ISIS; all changes, updates, or additions to Spring 2020 schedule will be in Campus Solutions by the CS Schedule team 8/28/2018.
2018-08-24 | Fri | Systems Support Analyst and Schedule Preparers | Run Schedule Report from ISIS
2019-08-26 | Mon | Systems Support Analyst | First download of spring 2020 schedule in CS
2019-08-26 | Mon | Systems Support Analyst | Send ISCLASS listings to Schedule Preparers
2019-08-28 | Wed | Schedule Preparers | Schedulers start entering Spring 2020 class schedule data in Campus Solutions as a group
2019-08-30 | Fri | Schedule Preparers | Begin producing Spring 2020 printer proofs from Campus Solutions
2018-08-13 | Mon | Jeff Mills, Systems Support Analyst | Run FDD 728 and email files to Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor.
September 2019
2019-09-02 | Mon | Holiday - Labor Day
2019-09-06 | Fri | Honors Coordinators – Wendy Smith & Leticia Lopez | Deliver changes to District Honors page to Multimedia Specialist
2019-09-06 | Fri | Dean, Online Instruction and Distributed Learning | Deliver changes to online learning common page (page prior to course listings) to Multimedia Specialist
2019-09-06 | Fri | Continuing Education Graphic Artist | Deliver Continuing Education pages (in pdf format) to Multimedia Specialist
2019-09-06 | Fri | Publications Editor & Supervisor | Email Sun Distributing list to PIOs for review and update
2019-09-06 | Fri | Public Information Officers | Return review Sun Distributing list to Publications Editor & Supervisor
2019-09-11 | Wed | Multimedia Specialist | Compile common pages and International Ed/Honors ads (in InDesign format) in case needed for schedule pagination
2019-09-11 | Wed | District Graphic Artist | Present draft of updated cover to Director
2019-09-13 | Fri | Schedule Preparers | Input last changes to class schedule in CS prior to download. No changes after 5:00 PM
2019-09-16 | Mon | Jeff Mills, Systems Support Analyst | Run ISCLASS run control in CS and email Schedule Preparers the listings
2019-09-16 | Mon | Eric Nunes, Multimedia Specialist | Email Military Ed listings and Online course listings to Schedule Preparers for review
2018-09-17 | Mon | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Schedule Website (after 8:30 AM)
2019-09-16 | Mon | Schedule Preparers | Print and distribute course listings. Coordinate review of CS content with department chairs and campus deans. Update content changes/corrections in CS. Report errors regarding title and short course descriptions to Instructional Services
2019-09-23 | Mon | TBD by each College | Deliver Changes to Off-Campus locations to Multimedia Specialist (City-Jeanie Tyler; Mesa-Arlis Svedberg; Miramar-Terrie Hubbard)
2019-09-25 | Wed | Student Systems Support Technician | Reviews first draft of narrative (First Review)
2019-09-25 | Wed | Eric Nunes, Multimedia Specialist | Notify Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2019-09-25 | Wed | Stephanie Bulger, Vice Chancellor, Instructional Services | Drop dead date to cancel printed schedule production
2019-09-26 | Thu | Student Systems Support Technician | First review changes due back to IS Multimedia Specialist (additional changes after this date may be made with SDCCD class schedule proofing sign-off form)
2019-09-27 | Fri | Schedule Preparers | Input final corrections to class schedule prior to final download. No changes after 5:00 PM. This is the final input deadline for CS data to be included in printed schedule. Any changes after 5pm will be reflected in online schedule, but not printed schedule1
2019-09-27 | Fri | Schedule Preparers | FINAL download for the printed Class Schedule from Campus Solutions
2019-09-27 | Fri | Eric Nunes, Multimedia Specialist | Email updated Military Ed page to Schedule Preparers and Director, Off-Campus Programs (Catherine Shafer).
2019-09-30 | Mon | Jeff Mills, Systems Support Analyst | Email course listings to Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor
2019-09-30 | Mon | Schedule Preparers | Begin final formatting of course listings in MS Word
2019-09-30 | Mon | Schedule Preparers | Colleges review class listings and make corrections in Campus Solutions
October 2019
2019-10-03 | Thur. | District Graphic Artist | Final cover art due. Beresford/Chancellor signoff
2019-10-03 | Thur. | Multimedia Specialist | Integrate changes to online listings from all three colleges into InDesign
2019-10-07 | Mon | Schedule Preparers | Deliver MS Word formatted course listings to PIOs (1st proof)
2019-10-07 | Mon | Schedule Preparers, Director of Off-Campus Programs | Email corrections to Military Ed page to Multimedia Specialist
2019-10-07 | Mon | Schedule Preparers | Add comments to online course listings file, make corrections/changes, and email file to Multimedia Specialist
2019-10-09 | Wed | Erica Marrone, Curriculum Analyst | Deliver Prerequisites changes to Student Systems Support Technician?
2019-10-10 | Thur. | Multimedia Specialist | Email online course listings PDF to Schedule Preparers for review
2019-10-14 | Mon | Information Officers | Deliver proofs to Schedule Preparers/VP Instruction-final review
2019-10-15 | Tue | Schedule Preparers | Return corrected page proofs to PIOs in AM, return online listings PDF with any changes to Multimedia Specialist
2019-10-15 | Tue | Erica Marrone, Curriculum Analyst | Download ISCLASS (using FDD 728) section comments for review. Send corrections to Schedule Preparers to update CS.
2018-10-16 | Tue | Information Officers / VP’s Instruction | Deliver campus pages in hard copy and InDesign digital file to Jeff Mills, Systems Support Analyst in the AM
2018-10-16 | Tue | Multimedia Specialist | Compiles sections of the combo and repaginates
2019-10-18 | Fri | Jeff Mills, Systems Support Analyst | Email request for campus quantities to VPSSs
2019-10-18 | Fri | Erica Marrone, Curriculum Analyst | Send section comments corrections to Schedule Preparers to update CS
2019-10-18 | Fri | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2019-10-18 | Fri | Student Systems Support Technician/Information Officers/Multimedia Specialist | Proof combo page proofs in Instructional Services-check calendars, narrative, and legal information specifically. Distribute, complete, and retain SDCCD sign-off forms. Update In Design files with help from System Support Analyst (Final Proof--All changes must be made by 5:00 pm)
2019-10-21 | Mon | Student Systems Support Technician | Post class schedule to the web. CS Online Class Schedule available to the public.
2019-10-23 | Wed | Vice Presidents of Student Services | Email campus quantities needed to Jeff Mills, Systems Support Analyst.
2019-10-23 | Wed | Mail Room Clerk | Prepare Postal Form for mailing combo schedules
2019-10-25 | Fri | Commercial Printer (Advantage, Inc.) | Pick up combo page proofs, digital files, cover art, from Instructional Services in the PM 2
2019-10-28 | Mon | Jeff Mills, Systems Support Analyst | Remind the Duplicating Supervisor to make sure that sufficient funds are in the postal account to cover the cost of the class schedule mailing
2019-10-28 | Mon | Commercial Printer (Advantage, Inc.) | Deliver combo schedule digital bluelines and cover color key to Instructional Services 2
2019-10-29 | Tue | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff. Final proofing. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2019-10-30 | Wed | Commercial Printer (Advantage, Inc.) | Pick up reviewed bluelines from Instructional Services
November 2019
2019-11-12 | Tue | Student Services | Tentative Priority Registration Date
2018-11-07 | Wed | Advantage, Inc. | Deliver combo schedules to District sites and Post Office, and minimum of 600 combo schedules to Student Services 2
2018-11-12 | Mon | Holiday - Veterans Day
December 2019
2018-12-06 | Thu | Jeff Mills, Systems Support Analyst | Check schedule quantities at the Warehouse
January 2020
2019-01-07 | Mon | Jeff Mills, Systems Support Analyst | Contact Warehouse to recycle remaining schedules
Student Services, District Headquarters
| Student Systems Support Technician |  | Danya Sanchez
| Student Services Analyst |  | Melonie Limtiaco
Instructional Services and Planning, District Headquarters
| Dean, Online Instruction & Learning |  | Kats Gustafson
| Dean, Worksforce Development |  | Amertah Perman
| Vice Chancellor, Instructional Services & Planning |  | Stephanie Bulger
| Systems Support Analyst |  | Jeff Mills
| Multimedia Specialist |  | Eric Nunes
| Curriculum Analyst |  | Erica Marrone
Communications and Public Relations, District Headquarters
| District Graphic Artist |  | Claudia Azcona-Mercado
| Publications Editor & Supervisor |  | Leslie Hackett
District Sites (Colleges and CE Campuses)
| IT Production Control |  | District/Miramar
| Information Officers (PIOs) |  | Cesar Gumapas (City)
Jennifer Kearns (Mesa)
Stephen Quis (Miramar)
Ranessa Ashton (Continuing Education)
| Graphic Artists |  | Kimberly La Rue (City)
Nicholas David (Mesa)
Joan Mize (Miramar)
| Schedule Preparers |  | Kamini Bhakta (City)
Arlis Svedberg (Mesa)
Melanie Cordero (Miramar)
Off-site Printers
| Advantage, Inc. |  | Advantage, Inc.
1Production staff (i.e. district and non-district personnel involved in producing class schedules) will not be held accountable for meeting production timelines for information or alterations to the schedule, which are submitted after 5:00 PM on this date.
2We attempt to arrange schedule delivery by 10:00 AM and pick up by 2:00 PM; however this is subject to change depending on conditions at the time. Please contact Instructional Services for more information.

## By Responsibility
Date |  | Responsibility | Activity
December 2017
2017-12-04 | Mon | Erica Marrone, Curriculum Analyst | Email CALT document to Schedule Preparers and request confirmation of dates
2017-12-18 | Mon | VPIs | Return CALT dates and parameters to Shelly Hess
2017-12-18 | Mon | Erica Marrone, Curriculum Analyst | Deliver CALT dates to Student Services
January 2018
2018-01-12 | Fri | Erica Marrone, Curriculum Analyst | Roll Spring 2018 to Spring 2020 in ISIS Scheduler Project Available for Input After the Roll
2018-01-15 | Mon | Student Services Analyst | Make Scheduler available (Melonie)
2018-01-15 | Mon | Department Chairs | Update Spring 2020 class information in ISIS/Scheduler
1/15 - 5/4 |  | Schedule Preparers | Update Spring 2020 class information in ISIS
2018-05-04 | Fri | Team of Schedule Preparers | Scheduler availability ends for Spring 2020
5/4 - 9/28 |  | Jeff Mills, Systems Support Analyst | Run B2511 and 2505 printers proofs for Spring 2020
5/4 - 9/28 |  | Team of Schedule Preparers | Use B2511 and B2505 printers proofs to enter Spring 2020 class data manually into Campus Solutions begins.
2018-06-08 | Fri | Schedule Preparers | END data entry for Spring 2020 class sections in ISIS
2018-06-19 | Tue | Schedule Preparers | Begin entering Spring 2020 class schedule data in Campus Solutions
2018-07-24 | Tue | IT Production Control? | Class Schedule Report available (replaces printers proofs)
2018-07-28 | Sat | Schedule Preparers | Last day for Spring 2020 class schedule data entry in Campus Solutions at Corporate Ed Center.
2018-11-07 | Wed | Advantage, Inc. | Deliver combo schedules to District sites and Post Office, and minimum of 600 combo schedules to Student Services 2
2019-10-25 | Fri | Commercial Printer (Advantage, Inc.) | Pick up combo page proofs, digital files, cover art, from Instructional Services in the PM 2
2019-10-28 | Mon | Commercial Printer (Advantage, Inc.) | Deliver combo schedule digital bluelines and cover color key to Instructional Services 2
2019-09-06 | Fri | Continuing Education Graphic Artist | Deliver Continuing Education pages (in pdf format) to Multimedia Specialist
2018-08-22 | Wed | Dean, Economic Development | Report any changes to Corporate Council logos to District Graphic Designer (Claudia)
2019-09-06 | Fri | Dean, Online Instruction and Distributed Learning | Deliver changes to online learning common page (page prior to course listings) to Multimedia Specialist
2019-08-15 | Thu | Director, Communications and Public Relations | Review Chancellor's Welcome Message and provide updates to Multimedia Specialist
2019-08-15 | Thu | District Graphic Artist | Select photos for cover
2019-09-11 | Wed | District Graphic Artist | Present draft of updated cover to Director
2019-10-03 | Thur. | District Graphic Artist | Final cover art due. Beresford/Chancellor signoff
2019-09-25 | Wed | Eric Nunes, Multimedia Specialist | Notify Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2019-09-27 | Fri | Eric Nunes, Multimedia Specialist | Email updated Military Ed page to Schedule Preparers and Director, Off-Campus Programs (Catherine Shafer).
2019-10-09 | Wed | Erica Marrone, Curriculum Analyst | Deliver Prerequisites changes to Student Systems Support Technician?
2019-10-15 | Tue | Erica Marrone, Curriculum Analyst | Download ISCLASS (using FDD 728) section comments for review. Send corrections to Schedule Preparers to update CS.
2019-10-18 | Fri | Erica Marrone, Curriculum Analyst | Send section comments corrections to Schedule Preparers to update CS
2019-09-02 | Mon | Holiday - Labor Day
2018-11-12 | Mon | Holiday - Veterans Day
2019-09-06 | Fri | Honors Coordinators – Wendy Smith & Leticia Lopez | Deliver changes to District Honors page to Multimedia Specialist
2019-08-23 | Fri | Schedule Preparers | END data entry for Spring class sections in ISIS; all changes, updates, or additions to Spring 2020 schedule will be in Campus Solutions by the CS Schedule team 8/28/2018.
2018-08-24 | Fri | Systems Support Analyst and Schedule Preparers | Run Schedule Report from ISIS
2019-08-26 | Mon | Systems Support Analyst | First download of spring 2020 schedule in CS
2019-08-26 | Mon | Systems Support Analyst | Send ISCLASS listings to Schedule Preparers
2019-10-14 | Mon | Information Officers | Deliver proofs to Schedule Preparers/VP Instruction-final review
2018-10-16 | Tue | Information Officers / VP’s Instruction | Deliver campus pages in hard copy and InDesign digital file to Jeff Mills, Systems Support Analyst in the AM
2018-08-13 | Mon | Jeff Mills, Systems Support Analyst | Run FDD 728 and email files to Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor.
2018-12-06 | Thu | Jeff Mills, Systems Support Analyst | Check schedule quantities at the Warehouse
2019-01-07 | Mon | Jeff Mills, Systems Support Analyst | Contact Warehouse to recycle remaining schedules
2019-09-16 | Mon | Jeff Mills, Systems Support Analyst | Run ISCLASS run contol in CS and email Schedule Preparers the listings
2019-09-30 | Mon | Jeff Mills, Systems Support Analyst | Email course listings to Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor
2019-10-18 | Fri | Jeff Mills, Systems Support Analyst | Email request for campus quantities to VPSSs
2019-10-28 | Mon | Jeff Mills, Systems Support Analyst | Remind the Duplicating Supervisor to make sure that sufficient funds are in the postal account to cover the cost of the class schedule mailing
2019-10-23 | Wed | Mail Room Clerk | Prepare Postal Form for mailing combo schedules
2018-10-16 | Tue | Multimedia Specialist | Compiles sections of the combo and repaginates
2019-09-11 | Wed | Multimedia Specialist | Compile common pages and International Ed/Honors ads (in InDesign format) in case needed for schedule pagination
2019-10-03 | Thur. | Multimedia Specialist | Integrate changes to online listings from all three colleges into InDesign
2019-10-10 | Thur. | Multimedia Specialist | Email online course listings PDF to Schedule Preparers for review
2019-10-18 | Fri | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff page proofs are available. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2019-10-29 | Tue | Multimedia Specialist | Notify campus Information Officers and Student Services’ staff. Final proofing. Distribute, complete, and retain SDCCD class schedule proofing sign-off forms.
2019-09-06 | Fri | Public Information Officers | Return review Sun Distributing list to Publications Editor & Supervisor
2019-09-06 | Fri | Publications Editor & Supervisor | Email Sun Distributing list to PIOs for review and update
2019-08-28 | Wed | Schedule Preparers | Schedulers start entering Spring 2020 class schedule data in Campus Solutions as a group
2019-08-30 | Fri | Schedule Preparers | Begin producing Spring 2020 printer proofs from Campus Solutions
2019-09-13 | Fri | Schedule Preparers | Input last changes to class schedule in CS prior to download. No changes after 5:00 PM
2019-09-16 | Mon | Schedule Preparers | Print and distribute course listings. Coordinate review of CS content with department chairs and campus deans. Update content changes/corrections in CS. Report errors regarding title and short course descriptions to Instructional Services
2019-09-27 | Fri | Schedule Preparers | Input final corrections to class schedule prior to final download. No changes after 5:00 PM. This is the final input deadline for CS data to be included in printed schedule. Any changes after 5pm will be reflected in online schedule, but not printed schedule1
2019-09-27 | Fri | Schedule Preparers | FINAL download for the printed Class Schedule from Campus Solutions
2019-09-30 | Mon | Schedule Preparers | Begin final formatting of course listings in MS Word
2019-09-30 | Mon | Schedule Preparers | Colleges review class listings and make corrections in Campus Solutions
2019-10-07 | Mon | Schedule Preparers | Deliver MS Word formatted course listings to PIOs (1st proof)
2019-09-16 | Mon | Eric Nunes, Multimedia Specialist | Email Military Ed listings and Online course listings to Schedule Preparers for review
2019-10-07 | Mon | Schedule Preparers | Add comments to online course listings file, make corrections/changes, and email file to Multimedia Specialist
2019-10-15 | Tue | Schedule Preparers | Return corrected page proofs to PIOs in AM, return online listings PDF with any changes to Multimedia Specialist
2019-10-07 | Mon | Schedule Preparers, Director of Off-Campus Programs | Email corrections to Military Ed page to Multimedia Specialist
2018-09-17 | Mon | Schedule Preparers, Distance Ed Coordinators, and Bookstore Supervisor | Download course listings/rich text reports/Access database file from ISCLASS Schedule Website (after 8:30 AM)
2019-09-25 | Wed | Stephanie Bulger, Vice Chancellor, Intsructional Services | Drop dead date to cancel printed schedule production
2018-11-08 | Wed | Student Services | Spring 2020 Registration begins
2018-12-17 | Mon | Student Services | Open Registration
2019-11-12 | Tue | Student Services | Priority Registration
2019-08-14 | Wed | Student Services Support Technician | Update Crosswalk Table X_ISCLASS_AE in CS Production environment
2019-08-14 | Wed | Student Services Support Technician | Deliver cover changes to District Graphic Artist
2019-08-23 | Fri | Student Systems Support Technician | Deliver highlighted changes in MS Word (final narrative, academic calendars/common pages, fee information, policy statements, etc. for Combo class schedules) to Multimedia Specialist
2019-09-25 | Wed | Student Systems Support Technician | Reviews first draft of narrative (First Review)
2019-09-26 | Thu | Student Systems Support Technician | First review changes due back to IS Multimedia Specialist (additional changes after this date may be made with SDCCD class schedule proofing sign-off form)
2019-10-28 | Mon | Student Systems Support Technician | Post class schedule to the web. CS Online Class Schedule available to the public.
2019-10-18 | Fri | Student Systems Support Technician/Information Officers/Multimedia Specialist | Proof combo page proofs in Instructional Services-check calendars, narrative, and legal information specifically. Distribute, complete, and retain SDCCD sign-off forms. Update In Design files with help from System Support Analyst (Final Proof--All changes must be made by 5:00 pm)
2019-09-23 | Mon | TBD by each College | Deliver Changes to Off-Campus locations to Multimedia Specialist (City-Jeanie Tyler; Mesa-Arlis Svedberg; Miramar-Terrie Hubbard)
2019-10-23 | Wed | Vice Presidents of Student Services | Email campus quantities needed to Jeff Mills, Systems Support Analyst.
Student Services, District Headquarters
| Student Systems Support Technician |  | Danya Sanchez
| Student Services Analyst |  | Melonie Limtiaco
Instructional Services and Planning, District Headquarters
| Dean, Online Instruction & Learning |  | Kats Gustafson
| Dean, Worksforce Development |  | Amertah Perman
| Vice Chancellor, Instructional Services & Planning |  | Stephanie Bulger
| Systems Support Analyst |  | Jeff Mills
| Multimedia Specialist |  | Eric Nunes
| Curriculum Analyst |  | Erica Marrone
Communications and Public Relations, District Headquarters
| District Graphic Artist |  | Claudia Azcona-Mercado
| Publications Editor & Supervisor |  | Leslie Hackett
District Sites (Colleges and CE Campuses)
| IT Production Control |  | District/Miramar
| Information Officers (PIOs) |  | Cesar Gumapas (City)
Jennifer Kearns (Mesa)
Stephen Quis (Miramar)
Ranessa Ashton (Continuing Education)
| Graphic Artists |  | Kimberly La Rue (City)
Nicholas David (Mesa)
Joan Mize (Miramar)
| Schedule Preparers |  | Kamini Bhakta (City)
Arlis Svedberg (Mesa)
Melanie Cordero (Miramar)
Off-site Printers
| Advantage, Inc. |  | Advantage, Inc.
1Production staff (i.e. district and non-district personnel involved in producing class schedules) will not be held accountable for meeting production timelines for information or alterations to the schedule, which are submitted after 5:00 PM on this date.
2We attempt to arrange schedule delivery by 10:00 AM and pick up by 2:00 PM; however this is subject to change depending on conditions at the time. Please contact Instructional Services for more information.

## By Milestones
Major Milestones for Spring 2020
Dates | Description
2019-05-31 | Roll Forward Spring 2018 to Spring 2019
2019-08-23 | Student Services Changes
2019-08-26 | First Download
2019-09-13 | Second Download
2019-09-25 | Last chance to cancel printed class schedule production
2019-09-25 | Student Services (1st Review)
2019-09-26 | Student Services 1st review due back to Instructional Services
2019-09-27 | Final Download for the printed class schedule
2019-10-14 | PIOs First Page Proof
2019-10-18 | Page Proofs Due
2018-10-17 | Review Final Page Proofs
2019-10-21 | Post CS Online Class Schedule
2019-10-30 | Bluelines to Printers (PIOs and Student Services Proof)
2019-11-07 | Schedules Delivered
2019-11-12 | Priority Registration (tentative)